## Q2 25
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT GOVERNMENT PROJECTS, PROGRAMS OR ACTIVITIES
Region: XI |  |  |  | Calender Year: | 2025
Province: Davao de Oro |  |  |  | Quarter: | 2
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Construction/Upgrading of CVPH-Pantukan | Brgy. Kingking, Pantukan | 46400000 | 2019-10-24 | 2021-08-27 | 100% | 46208841.483 |  | Completed
Construction/Upgrading of CVPH-Pantukan - Phase II | Brgy. Kingking, Pantukan | 3600000 | 2021-03-13 | 2021-08-27 | 100% | 3233322.99 |  | Completed
Const. of IP House (Balai Mandaya-Mansaka) | Brgy. Pagsabangan, New Bataan | 20000000 | 2020-02-20 | 2025-02-25 | 96.46% | 18550451.78 | 21 | ADMIN. On-going.
Const. of IP House (Balai Tu Mandiba) | Brgy. Prosperidad, Montevista | 20000000 | 2020-02-20 | 2025-02-25 | 98.3% | 18697330.13 | 21 | ADMIN. On-going.
Const. of IP House (Balai na Linagsawan Tu Tribu Dibabawon) | Brgy. Awao, Monkayo | 20000000 | 2020-02-20 | 2025-02-25 | 94.62% | 18191110.09 | 21 | ADMIN. On-going.
Const. of Temporary Treatment & Monitoring Facility | Kingking, Pantukan | 10000000 | 2022-03-30 | 2023-05-09 | 100% | 9994250.89 |  | Completed
Const. Of Water System at Barangay Maparat, Compostela | Maparat, Compostela | 20000000 | 2021-10-07 | 2022-12-31 | 100% | 10998534.4 |  | Completed
Road Upgrading/Improvement at Purok 1, Barangay Panansalan, Compostela | Purok 1, Panansalan, Compostela | 20000000 | 2021-09-07 | 2023-08-15 | 100% | 8825950.13 |  | Completed
Const. of Level II Water System, Barangay Masara | Masara, Maco | 3000000 | 2021-11-11 | 2022-06-24 | 100% | 0 |  | Completed
Improvement of Health Center Calabcab, Maco | Calabcab, Maco | 1500000 | 2021-11-11 | 2022-02-02 | 100% | 1347606.49 |  | Completed
Upgrading of Water Supply System, Brgy. Bahi | Bahi, Maragusan | 3000000 | 2021-11-25 | 2022-06-19 | 100% | 2699977.91 |  | Completed
Conc. of Purok Rizal FMR, Brgy. Coronobe, Maragusan | Coronobe, Maragusan | 5000000 | 2021-09-07 | 2022-01-07 | 100% | 4399975.03 |  | Completed
Rehab. of Prk. Del Pilar-Prk. Jacinto FMR, Barangay Coronobe, Maragusan | Coronobe, Maragusan | 5000000 | 2021-09-07 | 2022-04-30 | 100% | 4499968.59 |  | Completed
Const. of Water Supply System, Brgy. San Jose, Monkayo | San Jose, Monkayo | 13000000 | 2021-10-07 | 2023-02-26 | 100% | 13000000 |  | Completed
Const. of Water Supply System, Brgy. San Isidro, Monkayo | San Isidro, Monkayo | 10000000 | 2021-10-07 | 2023-03-20 | 100% | 7997328.15 |  | Completed
Rehab/Improvement of Water Supply System at Brgy Mt. Diwata, Monkayo | Mount Diwata, Monkayo | 10000000 | 2021-11-25 | 2023-02-10 | 100% | 8499953.13 |  | Completed
Establishment of Feedmills | Pasian, Monkayo | 7500000 | 2019-11-28 | 2025-12-31 | 81.37% | 6103000 |  | Waiting for the completion of Phase 2
Procurement and Delivery of Trichoderma Packs (Support to Fusarium Wilt Mgt) | Provincewide | 5761600 | 2024-01-01 | 2024-12-31 | 37.24% | 2145863.94 |  | On going
Establishment of Multiplier Farm | Pasian, Monkayo | 5627255.16 | 2020-08-22 | 2025-03-31 | 100% | 5627255.16 |  | Completed
AFC Support Fund/Consultation Fund 2024 | Provincewide | 140000 | 2024-05-29 | 2025-04-30 |  | 0 |  | On going
Sustainment of Molecular Laboratory Operation | DDOPH-Montevista | 5000000 | 2003-12-04 | 2024-06-30 | 27.78% | 1388800 |  | Completed
Health Emergency Allowance (HEA)/OCA | Provincewide | 90354375 | 2024-05-29 | 2024-12-31 | 100% | 90354375 |  | Completed
Share in PCSO-Lotto LGU Share | Provincewide | 654675.2 | 2023-07-01 | 2024-12-31 | 44.76% | 293060.77 |  | On going
Establishment of 30 SOW Level Swine Multiplier Farm (INSPIRE) Program | Provincewide | 10000000 | 2023-12-15 | 2025-12-31 | 50.29% | 5028928.29 |  | On going
PAFES Operation Fund for Co-Financing in DDO 2023-2025 | Provincewide | 875000 | 2023-07-27 | 2025-06-30 | 99.75% | 872855 |  | Completed
Community Empowered through Science & Technology | Provincewide | 1500000 | 2023-12-10 | 2025-12-10 | 69.16% | 1037385 |  | On going
Livestock & Poultry Dev't. Program (Impv't. of Free-Ranged Chicken Production Facility) | Pasian, Monkayo | 100000 | 2024-04-22 | 2025-03-31 | 100% | 100000 |  | Completed
Brgy. Watershed Reforestation & Rehab.Project-Prk.5, Sitio Pinaupuan, Naga, Laak | Naga, Laak | 100000 | 2024-04-22 | 2024-07-22 | 100% | 100000 |  | Completed
Brgy. Watershed Reforestation & Rehab. Project-Prk.7, Sitio Cadan, Kapitunan, Nabunturan | Katipunan, Nabunturan | 100000 | 2024-04-22 | 2024-07-22 | 100% | 100000 |  | Completed
Brgy. Watershed Reforestation & Rehab. Project-Prk.12, San Miguel, Compostela | San Miguel, Compostela | 100000 | 2024-04-22 | 2024-07-22 | 100% | 100000 |  | Completed
Brgy. Watershed Reforestation & Rehab. Project-Prk.15, Bantacan, New Bataan | Bantacan, New Bataan | 100000 | 2024-04-22 | 2024-07-22 | 100% | 100000 |  | Completed
Brgy. Watershed Reforestation & Rehab. Project-Sitio Lanzones, Lahi, Maragusan | Lahi, Maragusan | 100000 | 2024-04-22 | 2024-07-22 | 100% | 100000 |  | Completed
Medical Assistance to Indigent and Financially Incapacitated Patients | Provincewide | 37746000 | 2024-09-25 | 2024-12-31 | 99.47% | 37544137.31 |  | Completed
Emergency Employment Program 2024-TUPAD | Provincewide | 44581801 | 2024-11-01 | 2025-12-31 | 64.22% | 28629953.54 |  | On going
Assistance to Individual in Crisis Situation (AICS) 2024 | Provincewide | 10000000 | 2024-12-17 | 2025-12-17 | 100% | 10000000 |  | Completed
Trichoderma Harzianum Project under HVCDP CY 2024 | Provincewide | 1144000 | 2025-01-22 | 2026-02-16 | 7.243% | 82864 |  | On going
QRF 2024 (Rehab. & Recovery of Shearline & Low Pressure Area (LPA) affected farmers | Provincewide | 8471420 | 2025-01-22 | 2026-01-22 |  |  |  | On going
Implementation of Healthy Learning Institutions | Provincewide | 3700000 | 2025-03-03 | 2025-12-29 |  |  |  | On going
Healthy Communities | Provincewide | 4297964 | 2025-03-05 | 2025-12-29 | 10.56% | 454000 |  | On going
Assistance to Individual in Crisis Situation (AICS) 2025 | Provincewide | 30000000 | 2025-05-02 | 2025-12-30 | 8.793% | 2637905 |  | On going
Medical Assistance to Indigent and Financially Incapacitated Patients | Provincewide | 40097000 | 2025-06-04 | 2025-12-30 |  |  |  | On going
0
| TOTAL | 518551090.36 |  |  |  | 369944984.203
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
(SGD.)ARIEL D. MANDAWE, CPA | (SGD.)EVA JEAN S. LICAYAN |  | (SGD.)ENGR. RODERICK M. DIGAMON |  |  | (SGD.)ENGR. RAUL G. MABANGLO
Provincial Accountant | Provincial Budget Officer |  | Provincial Engineer |  |  | Governor