## Q3 24
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT GOVERNMENT PROJECTS, PROGRAMS OR ACTIVITIES
Region: XI |  |  |  | Calender Year: | 2024
Province: Davao de Oro |  |  |  | Quarter: | 3
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Construction/Upgrading of CVPH-Pantukan | Brgy. Kingking, Pantukan | 46400000 | 2019-10-24 | 2021-08-27 | 100% | 41617957.33 |  | Completed
Construction/Upgrading of CVPH-Pantukan - Phase II | Brgy. Kingking, Pantukan | 3600000 | 2021-03-13 | 2021-08-27 | 100% | 3233322.99 |  | Completed
Const. of IP House (Balai Mandaya-Mansaka) | Brgy. Pagsabangan, New Bataan | 20000000 | 2020-02-20 | 2023-10-28 | 95.57% | 15347073.49 | 21 | ADMIN. Materials only. Lumber, CHB and construction supplies delivered. R.I.S on process. (To be used for landmark and water system).
Const. of IP House (Balai Tu Mandiba) | Brgy. Prosperidad, Montevista | 20000000 | 2020-02-20 | 2023-10-28 | 95.64% | 15000000 | 21 | ADMIN. Materials only. Lumber delivered. Construction supplies waiting for the delivery. Chloring Purchase Request on process. (To be used for landmark and water system).
Const. of IP House (Balai na Linagsawan Tu Tribu Dibabawon) | Brgy. Awao, Monkayo | 20000000 | 2020-02-20 | 2023-10-28 | 84.39% | 15344654.49 | 21 | ADMIN. Materials only. Lumber, CHB and construction supplies delivered. R.I.S on process. (To be used for landmark and water system).
Const. of Temporary Treatment & Monitoring Facility | Kingking, Pantukan | 10000000 | 2022-03-30 | 2023-05-09 | 100% | 8495113.26 |  | Completed
Road Upgrading/Improvement at Purok Side 4, Barangay Mangayon, Compostela | Purok Side 4, Mangayon, Compostela | 20000000 | 2021-08-31 | 2022-08-19 | 100% | 20000000 |  | Completed
Const. Of Water System at Barangay Maparat, Compostela | Maparat, Compostela | 20000000 | 2021-10-07 | 2022-12-31 | 100% | 10998534.4 |  | Completed
Road Upgrading/Improvement at Purok 1, Barangay Panansalan, Compostela | Purok 1, Panansalan, Compostela | 20000000 | 2021-09-07 | 2023-08-15 | 100% | 8825950.13 |  | Completed
Road Upgrading/Improvement Purok 4 to Purok 6, Barangay San Jose, Compostela | Purok 4-6, San Jose, Compostela | 20000000 | 2021-09-07 | 2022-08-02 | 100% | 20000000 |  | Completed
Road Upgrading/Improvement Purok 3, Barangay Tamia, Compostela | Purok 3, Tamia, Compostela | 20000000 | 2021-07-27 | 2022-08-20 | 100% | 20000000 |  | Completed
Upgrading of FMR at Barangay Datu Davao, Laak | Datu Davao, Laak | 12000000 | 2021-08-31 | 2022-06-09 | 100% | 12000000 |  | Completed
Const. of Water System at Barangay Datu Davao, Laak. | Datu Davao, Laak | 6000000 | 2021-11-29 | 2022-08-04 | 100% | 2546700.28 |  | Completed
Const. of Evacuation Center at Barangay Kapatagan, Laak | Kapatagan, Laak | 3000000 | 2021-10-07 | 2022-04-02 | 100% | 3000000 |  | Completed
Upgrading/Improvement of FMR at Barangay Kapatagan, Laak. | Kapatagan, Laak | 7000000 | 2021-08-31 | 2022-02-16 | 100% | 7000000 |  | Completed
Upgrading/Improvement of Candinuyan-Barigyan FMR, Golden Valley, Mabini | Golden Valley, Mabini | 10000000 | 2021-07-25 | 2022-01-18 | 100% | 10000000 |  | Completed
Upgrading/Improvement of Settler-Shanghai-Dasuran FMR, Mabini | Golden Valley, Mabini | 4000000 | 2021-07-25 | 2022-01-11 | 100% | 4000000 |  | Completed
Upgrading/Improvement of Bucana-Mambatang FMR | Anitapan, Mabini | 14000000 | 2021-07-25 | 2022-06-23 | 100% | 14000000 |  | Completed
Const. of Water System (Migum-Lower B), Barangay Cabuyuan | Cabuyuan, Mabini | 5000000 | 2021-10-07 | 2022-05-23 | 100% | 5000000 |  | Completed
Upgrading/Improvement of FMR at Barangay Gubatan, Maco | Gubatan, Maco | 9000000 | 2021-07-25 | 2022-06-25 | 100% | 9000000 |  | Completed
Const. of Level II Water Supply System at Barangay Gubatan, Maco | Gubatan, Maco | 5000000 | 2021-12-25 | 2022-06-21 | 100% | 5000000 |  | Completed
Sitio Electrification at Barangay Gubatan | Gubatan, Maco | 3000000 | 2022-02-15 | 2022-06-02 | 100% | 3000000 |  | Completed
Const. of School Building, Barangay Masara, Maco | Masara, Maco | 3000000 | 2021-12-06 | 2022-04-15 | 100% | 3000000 |  | Completed
Const. of Level II Water System, Barangay Masara | Masara, Maco | 3000000 | 2021-11-11 | 2022-06-24 | 100% | 0 |  | Completed
Const. of Level II Water System at Barangay Calabcab, Maco | Calabcab, Maco | 10000000 | 2021-11-11 | 2022-10-01 | 100% | 10000000 |  | Completed
Improvement of Health Center Calabcab, Maco | Calabcab, Maco | 1500000 | 2021-11-11 | 2022-02-02 | 100% | 1347606.49 |  | Completed
Sitio Electrification, Barangay Sangab, Maco | Sangab, Maco | 4000000 | 2021-11-25 | 2022-06-30 | 100% | 4000000 |  | Completed
Const. of Level II Water System, Brgy. Sangab, Maco | Sangab, Maco | 5000000 | 2021-11-25 | 2022-09-05 | 100% | 5000000 |  | Completed
Const. of Level II Water System, Brgy. New Asturias | New Asturias, Maco | 8000000 | 2021-11-15 | 2023-03-30 | 100% | 8000000 |  | Completed
Const. of School Building, Brgy. New Asturias | New Asturias, Maco | 2000000 | 2021-11-15 | 2022-05-10 | 100% | 2000000 |  | Completed
Road Concreting of Purok 4 and 5, Brgy. New Asturias, Maco | New Asturias, Maco | 5000000 | 2021-10-07 | 2022-02-21 | 100% | 5000000 |  | Completed
Const. of Health Station, Brgy. Magangit, Maco | Magangit, Maco | 2500000 | 2021-08-24 | 2021-12-20 | 100% | 2500000 |  | Completed
Upgrading of Water Supply System, Brgy. Bahi | Bahi, Maragusan | 3000000 | 2021-11-25 | 2022-06-19 | 100% | 2699977.91 |  | Completed
Upgrading of Water Supply System, Brgy. Mahayahay, Maragusan | Mahayahay, Maragusan | 2500000 | 2021-10-24 | 2022-01-22 | 100% | 2500000 |  | Completed
Conc. of Purok Rizal FMR, Brgy. Coronobe, Maragusan | Coronobe, Maragusan | 5000000 | 2021-09-07 | 2022-01-07 | 100% | 4399975.03 |  | Completed
Rehab. of Prk. Del Pilar-Prk. Jacinto FMR, Barangay Coronobe, Maragusan | Coronobe, Maragusan | 5000000 | 2021-09-07 | 2022-04-30 | 100% | 4499968.59 |  | Completed
Upgrading of Water Supply System, Brgy. Katipunan, Maragusan | Katipunan, Maragusan | 5000000 | 2021-11-25 | 2022-03-21 | 100% | 5000000 |  | Completed
Upgrading of Farm to Market Road at Purok 6 Brgy. Andili, Mawab | Andili, Mawab | 20000000 | 2021-09-30 | 2023-01-19 | 100% | 20000000 |  | Completed
Const. of Water Supply System, Brgy. Casoon | Casoon, Monkayo | 20000000 | 2021-12-02 | 2023-02-28 | 100% | 20000000 |  | Completed
Const. of Water Supply System, Brgy. San Jose, Monkayo | San Jose, Monkayo | 13000000 | 2021-10-07 | 2023-02-26 | 100% | 6498205.39 |  | Completed
Upgrading/Improvement of FMR at Brgy. San Jose, Monkayo | San Jose, Monkayo | 7000000 | 2021-09-30 | 2023-02-05 | 100% | 7000000 |  | Completed
Const. of Water Supply System, Brgy. San Isidro, Monkayo | San Isidro, Monkayo | 10000000 | 2021-10-07 | 2023-03-20 | 100% | 7997328.15 |  | Completed
Road Upgrading at Brgy. San Isidro, Monkayo | San Isidro, Monkayo | 10000000 | 2021-07-20 | 2022-08-04 | 100% | 10000000 |  | Completed
Const. of Water Supply System, Brgy. Upper Ulip, Monkayo | Upper Ulip, Monkayo | 10000000 | 2021-11-25 | 2023-01-18 | 100% | 10000000 |  | Completed
Rehab/Improvement of Water Supply System at Brgy Mt. Diwata, Monkayo | Mount Diwata, Monkayo | 10000000 | 2021-11-25 | 2023-02-10 | 100% | 8499953.13 |  | Completed
Upgrading/Improvement of FMR at Brgy. San Vicente, Montevista | San Vicente, Montevista | 20000000 | 2021-10-07 | 2022-09-13 | 100% | 20000000 |  | Completed
Upgrading/Improvement of FMR at Brgy. Magsaysay, Nabunturan | Magsaysay, Nabunturan | 20000000 | 2021-08-31 | 2022-09-25 | 100% | 20000000 |  | Completed
Upgrading/Improvement of FMR at Brgy. Andap, New Bataan | Andap, New Bataan | 20000000 | 2021-11-25 | 2023-12-06 | 100% | 20000000 |  | Completed
Upgrading/Improvement of FMR at Brgy. Bantacan, New Bataan | Bantacan, New Bataan | 20000000 | 2021-09-07 | 2023-05-21 | 100% | 20000000 |  | Completed
Upgrading/Improvement of FMR at Brgy. Cabinuangan, New Bataan | Cabinuangan, New Bataan | 20000000 | 2021-07-21 | 2023-03-28 | 100% | 20000000 |  | Completed
Electrification project at Barangay Manurigao, New Bataan | Manurigao, New Bataan | 20000000 | 2021-12-02 | 2023-10-15 | 100% | 20000000 |  | Completed
Upgrading/Improvement of FMR at Brgy. Pagsabangan, New Bataan | Pagsabangan, New Bataan | 20000000 | 2021-08-31 | 2023-03-15 | 100% | 20000000 |  | Completed
Upgrading/Improvement of FMR at Brgy. Kingking, Pantukan | Kingking, Pantukan | 20000000 | 2021-08-30 | 2022-09-14 | 100% | 20000000 |  | Completed
Improvement of "Ginintuang Paraiso" Public Park, Provincial Capitol Complex | Cabidianan, Nabunturan | 20000000 | 2023-05-10 | 2023-12-30 | 100% | 20000000 |  | Completed
Establishment of Feedmills | Pasian, Monkayo | 7500000 | 2019-11-28 | 2024-12-15 | 81.37% | 6103000 |  | Waiting for the completion of Phase 2
AFC Support Fund/Consultation Fund 2023 | Provincewide | 140000 | 2023-08-04 | 2024-08-04 | 99.98% | 139970 |  | Completed
Trichoderma Harzianum Project under HVCDP CY 2023 | Provincewide | 649250 | 2023-10-01 | 2024-11-01 | 33.37% | 216646 |  | Completed
Procurement and Delivery of Trichoderma Packs (Support to Fusarium Wilt Mgt) | Provincewide | 5761600 | 2024-01-01 | 2024-12-31 | 5.43% | 312855.61 |  | On going
Establishment of Multiplier Farm | Pasian, Monkayo | 5627255.16 | 2020-08-22 | 2022-12-31 | 98.31% | 5532353.24 |  | Completed
AFC Support Fund/Consultation Fund 2024 | Provincewide | 140000 | 2024-05-29 |  |  |  |  | Project design on process
Medical Assistance to Indigent Patient (MAIP) | Provincewide | 168812500 | 2023-03-15 | 2024-12-30 | 97.55% | 164683390.67 |  | On going
Implementation of Adoloscent Health and Development Program | Provincewide | 500000 | 2021-10-21 | 2022-10-21 | 100% | 500000 |  | Completed
Meals, Accomodation & Transportation Allowance (MAT) Benefits | Provincewide | 3843000 | 2022-05-18 | 2023-06-18 | 100% | 3843000 |  | Completed
Sustainment of Molecular Laboratory Operation | DDOPH-Montevista | 5000000 | 2003-12-04 | 2024-06-30 | 0% | 0 |  | On going
2022-Health Emergency Allowance (HEA)/OCA | Provincewide | 7788187.5 | 2023-11-13 | 2024-03-13 | 100% | 7788187.5 |  | Completed
Health Promotion Playbook (PA 6) | Provincewide | 500000 | 2023-08-30 | 2024-08-30 | 100% | 500000 |  | On going
Health Emergency Allowance (HEA)/OCA | Provincewide | 90354375 | 2024-05-29 | 2024-12-31 | 94.33% | 85232098.32 |  | On going
Gov't. Intership Program and Emergency Employment 2022 | Provincewide | 26751998 | 2022-11-03 | 2024-09-30 | 94.99% | 25410941.66 |  | Completed
Share in PCSO-Lotto LGU Share | Provincewide | 493075.34 | 2023-07-01 | 2024-12-31 | 59.44% | 293060.77 |  | On going
Establishment of 30 SOW Level Swine Multiplier Farm (INSPIRE) Program | Provincewide | 10000000 | 2023-12-15 | 2024-12-15 | 2.946% | 294606.25 |  | On going
PAFES Operation Fund for Co-Financing in DDO 2023-2025 | Provincewide | 875000 | 2023-07-27 | 2024-09-30 | 56.13% | 491125 |  | On going
Assistance to Individual in Crisis Situation (AICS) 2024 | Provincewide | 20000000 | 2024-02-14 | 2024-12-31 | 95.18% | 19035281.5 |  | On going
Early Childhood Care and Development Council | Provincewide | 116000 | 2023-12-29 | 2024-12-29 | 50% | 58000 |  | On going
Community Empowered through Science & Technology | Provincewide | 1500000 | 2023-12-10 | 2024-12-10 | 0.992% | 14880 |  | On going
Livestock & Poultry Dev't. Program (Impv't. of Free-Ranged Chicken Production Facility) | Pasian, Monkayo | 100000 | 2024-04-22 | 2025-07-22 |  |  |  | For Purchse Request
Brgy. Watershed Reforestation & Rehab.Project-Prk.5, Sitio Pinaupuan, Naga, Laak | Naga, Laak | 100000 | 2024-04-22 | 2025-07-22 |  |  |  | Materials already delivered to watershed area.
Brgy. Watershed Reforestation & Rehab. Project-Prk.7, Sitio Cadan, Kapitunan, Nabunturan | Katipunan, Nabunturan | 100000 | 2024-04-22 | 2025-07-22 |  |  |  | Materials already delivered to watershed area.
Brgy. Watershed Reforestation & Rehab. Project-Prk.12, San Miguel, Compostela | San Miguel, Compostela | 100000 | 2024-04-22 | 2025-07-22 |  |  |  | Materials already delivered to watershed area.
Brgy. Watershed Reforestation & Rehab. Project-Prk.15, Bantacan, New Bataan | Bantacan, New Bataan | 100000 | 2024-04-22 | 2025-07-22 |  |  |  | Materials already delivered to watershed area.
Brgy. Watershed Reforestation & Rehab. Project-Sitio Lanzones, Lahi, Maragusan | Lahi, Maragusan | 100000 | 2024-04-22 | 2025-07-22 |  |  |  | Materials already delivered to watershed area.
Medical Assistance to Indigent and Financially Incapacitated Patients | Provincewide | 37746000 | 2024-09-25 | 2024-12-31 |  |  |  | On going
0
| TOTAL | 1037198241 |  |  |  | 903801717.58
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
(SGD.)ARIEL D. MANDAWE, CPA | (SGD.)EVA JEAN S. LICAYAN |  | (SGD.)ENGR. RODERICK M. DIGAMON |  |  | (SGD.)DOROTHY P. MONTEJO-GONZAGA
Provincial Accountant | Provincial Budget Officer |  | Provincial Engineer |  |  | Governor